## TestPlan
Test Planner and Tracker			TEAM 16	Raghu Ram Vadapalli, Vishal Batchu, Nikhil Tadigoppula, Syamantak Das
Test / No. ID	Related / Use case	Pre-conditions	Test Description (steps)	Expected Outcome	R1 Outcome (color code / cell background)	Comments (if test case failed)	R2 Outcome (color code / cell background)	Comments (if test case failed)
1	Design Class Diagrams	None	1.Check and make sure the classes work well together and if they are well defined.	A finished design diagram.
2	Start main game	1.A new game has been started.	1.Start the main game and displays the level selected after the user starts a new game.	Allows user to play game.
3	Start main game	1.A new game has been started.	1.User clicks on a piece and drags it. 2.He then drops it in a place which is not empty (Either there is another piece in that place or the piece does not fit completely).	The piece should not be placed in the location and be moved back to its original location from where it was picked up.
4	Start main game	1.A new game has been started.	1.User clicks on a piece and drags it. 2.He then drops it in an empty spot on the board in which this piece can fit.	The piece should now be positioned on the board where the user placed the piece.
5	Start new game	1.App launched	1.User clicked on Start game button. 2.They then proceed to choose a game mode and a level.	Game mode selected and level selection is displayed.		Planned for R2
6	View scores	1.App launched	1.User clicks on 'Leaderboard' button to access scores of other players.	High scores and Recent scores are displayed		Planned for R2
7	Select Level	1.A new game has been started. 2.A game mode has been selected.	1.User selects a level and then the game starts	Game mode selected and level selection is displayed.		Planned for R2
8	Score display	1.A main game has been started and completed successfully	1.User is displayed the score they achieved as soon as they complete a level.	Score for finished level is displayed		Planned for R2
9	Facebook Login	1.Connected to internet. 2.App launched.	1.User clicks on 'Facebook' and then enters their username and password and clicks on login to connect to their facebook account.	Successfully logged in and linked the account		Planned for R2
10	Facebook friend invites	1.Connected to facebook. 2.App launched.	1.User clicks on 'Invite Friends'. 2.Then selects a list of friends they would like to invite. 3.Press 'Send Invites' to invite them.	Successfully invited friends to play the game.		Planned for R2
11	Invite Bonuses	1.Connected to facebook. 2.App launched. 3.Has invited atleast 1 friend.	1.When an invite has been accepted, the user gets a bonus which he can use during the game (This may be a hint or a powerup).	Friends who accepted invites join game and user gets bonus		Planned for Post-R2
12	Feedback	1.App launched. 2.Connected to the internet.	1.User clicks on 'Send Feedback' from the main menu or after they finish a level where they enter their message and their details. 2.Then they press send to send the message to the developers.	Feedback has been sent to the game developers		Planned for Post-R2
13	Gain Achievements	1.App launched. 2.Has completed an achievement.	1.On completing certain tasks the user gains achievements (This is a popup which the user can see and acknowledge).	User has earned an achievement successfully and it shows up on their achievements page.		Planned for Post-R2
14	View Achievements	1.App launched	1.User clicks on 'Achievements' from where they can see all their present achievements and the ones that are still locked.	Game mode selected and level selection is displayed		Planned for Post-R2

## Instructions
Test plan Instructions

It is particularly important that you create a substantial set of Acceptance
Tests. These are tests based on the requirements document. Each acceptance
test should describe an operation to be performed by the user, and the
expected outcomes from that operation. The objective is to define a
comprehensive set of tests that between them cover all the features in the
requirements document. The tests should preferably cover all the frequent
"normal use" scenarios, as well as commonly occurring exception scenarios.
Each acceptance test must be described as a set of user instructions for
performing the test, much like a user manual. The outcomes description
specifies how the user knows whether the test succeeded or failed. The
reason for defining acceptance tests early in the life-cycle is to
facilitate "test-driven development". Developers can look at the acceptance
tests that their module must satisfy, and thereby know exactly what behavior
is expected from their module. Make sure to update these if/when
requirements change. Make sure to follow the suggested format.

## Monopoly Example
Monopoly Test Planner and Tracker (example)
	Game in test mode implies that the tester can control the outcome of the dice roll - assume dice roll can exceed 12 for testing.
	Note that some of the test cases require previous test cases to be completed as a precondition.
Acceptance tests

Test No.	User Story covered	Preconditions	Test Description	Expected Outcome	R1 Outcome	R2 Outcome
1	Move Player	Game is in test mode. / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester1	Player 1 Dice Roll Total : 5 / Player 1 End Turn	Player 1 is located at Reading Railroad cell.
2	Move Player	Test 1 completed	Player 1 Dice Roll Total : 5 / Player 1 End Turn	Player 1 is located on Jail cell.
3	Move Players in Turns	Game is in test mode. / Game is in initial state. / Number of Players: 2 / Player 1 Name: Tester1 / Player 2 Name: Tester2	Player 1 Dice Roll: 5 / Player 1 End Turn	Player 1 is located at Reading Railroad
			Player 2 Dice Roll: 3 / Player 2 End Turn	Player 2 is located at Baltic Avenue
4	Pass Go	Game is in test mode. / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester 1	Player 1 Dice Roll: 39 / Player 1 End Turn	Player 1 is located at Boardwalk
			Verify Player 1 bank balance	Player 1 has $1500
5	Pass Go	Game is in test mode / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester 1	Player 1 Dice Roll: 40 / Player 1 End Turn	Player 1 is located on GO cell
			Verify Player 1 bank balance	Player 1 has $1700	Go money paid out only after passing GO, not when it is reached.
6	Pass Go	Game is in test mode. / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester 1	Player 1 Dice Roll: 41 / Player 1 End Turn	Player 1 is located at / Mediterranean Avenue
			Verify Player 1 bank balance	Player 1 has $1700